## Template
| Gantt Chart | Malawi: Blood Giving Sets
BME 462 |  | START DATE |  | 2024-09-02 | COMPLETION BY TIME | 95.79% | DATE SHIFT |  |  | 1
|  | COMPLETION DATE |  | 2024-12-06 | COMPLETION BY STAGES | 100%
PROJECT DATA | [5 empty] | % COMPLETE | GANTT CHART
[7 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
STATUS | TASK | START DATE | DURATION, days | COMPLETION DATE | PERFORMER | PERCENTAGE OF EXECUTION | time axis 2024-09-02 to 2024-12-07
Initiation | [5 empty] | 100%
Completed | WA 1: Team Charter | 2024-09-02 | 1 | 2024-09-03 | All | 100%
Completed | Schedule Client Meetings | 2024-09-02 | 7 | 2024-09-09 | All | 100%
Completed | WA 2: Interview | 2024-09-03 | 7 | 2024-09-10 | All | 100%
Completed | Access to Student Shop | 2024-09-01 | 14 | 2024-09-15 | Hannah, Jason | 100%
Planning and Design | [5 empty] | 100%
Completed | Research: Community | 2024-09-02 | 7 | 2024-09-09 | Hannah, Jason | 100%
Completed | Research: Materials | 2024-09-02 | 7 | 2024-09-09 | Darcy, Michaela | 100%
Completed | WA 3: Community context, needs statement, and design criteria | 2024-09-10 | 7 | 2024-09-17 | All | 100%
Completed | Define Design Criteria (Initial Prototype) | 2024-09-16 | 7 | 2024-09-23 | All | 100%
Completed | Initial Brainstorming session | 2024-09-16 | 7 | 2024-09-23 | All | 100%
Completed | Oral Presentation #1 (hear) | 2024-09-16 | 7 | 2024-09-23 | All | 100%
Completed | Acquire Initial Materials | 2024-09-19 | 10 | 2024-09-29 | All | 100%
Completed | WA 4: Design solutions: prior art and lit review, brainstorming solutions, trade study between them, initial prototype 1 or sketches | 2024-09-21 | 10 | 2024-10-01 | All | 100%
Completed | Trade Study | 2024-09-23 | 7 | 2024-09-30 | All | 100%
Completed | Initial Prototype | 2024-09-23 | 14 | 2024-10-07 | All | 100%
Execution | [5 empty] | 100%
Completed | Medium Fidelity Prototype Iteration | 2024-10-07 | 14 | 2024-10-21 | All | 100%
Completed | MUBAS Connection and Collaborations | 2024-10-07 | 45 | 2024-11-21 | All | 100%
Completed | Blue Smith Inital Prints | 2024-10-07 | 7 | 2024-10-14 | All | 100%
Completed | Oral presentation #2 (create) | 2024-10-17 | 5 | 2024-10-22 | All | 100%
Completed | Blue Smith Re-Print | 2024-10-17 | 7 | 2024-10-24 | All | 100%
Completed | WA 5: Testing plan, prototype development and progress | 2024-10-17 | 12 | 2024-10-29 | All | 100%
Completed | Conduct Testing | 2024-10-29 | 21 | 2024-11-19 | All | 100%
Completed | Client Check in | 2024-10-28 | 5 | 2024-11-02 | All | 100%
Completed | WA 6: Testing report, iteration plan | 2024-10-29 | 21 | 2024-11-19 | All | 100%
Completed | High Fidelity Prototype iteration | 2024-11-12 | 7 | 2024-11-19 | All | 100%
| Activity 4 |  |  |  |  | 0%
Finalization & Handoff | [5 empty] | 100%
Completed | Final prototype | 2024-11-19 | 7 | 2024-11-26 | All | 100%
Not started | High Fidelity Prototype Testing* | 2024-11-19 | 18 | 2024-12-07 |  | 0% | 2024-09-02: * Plan to continute prototype and high fidelity testing next semester
Completed | Client Check in | 2024-11-18 | 5 | 2024-11-23 | All | 100%
Completed | WA 7: Training, handoff, continuation plan | 2024-11-12 | 21 | 2024-12-03 | All | 100%
Completed | WA 8: Poster draft | 2024-11-12 | 14 | 2024-11-26 | All | 100%
Final Presentation | [5 empty] | 0%
Completed | Final Poster | 2024-11-26 | 10 | 2024-12-08 | All | 100%
In process | Final Presentation | 2024-11-28 | 7 | 2024-12-05 | All | 0%
Not started | Final Client Meeting | 2024-11-28 | 7 | 2024-12-05 | All | 0%
| Activity 3 |  |  |  |  | 0%

## Лист2 (hidden)
In process
Completed
Not started
Suspended